## Overall
Project_ID | Country | Project Name | Project Status | Project Lifecycle | Budget | Spend | Start Date | Expected End Date | Runtime Left (Days)
1 | FRA | EMEA Connected City | Amber | Business Case Development | 218909 | 181694.47 | 1/10/2017 | 1/10/2017 | 5
2 | DEU | Rocket Space | Red | Business Case Development | 495672 | 614633.28 | 1/1/2017 | 1/9/2018 | 340
3 | DNK | Plug & Play | Amber | Business Case Development | 598511 | 538659.9 | 1/7/2017 | 1/9/2017 | -25
4 | SWE | Tempest | Amber | Testing | 562975 | 540456 | 1/3/2017 | 1/10/2017 | 5
5 | GBR | DADu (Daily Duties) IBM | Red | Developing | 204783 | 217069.98 | 1/11/2017 | 1/11/2018 | 401
6 | CHE | Trusted Traveller Programme | Green | Developing | 166661 | 81663.89 | 1/11/2017 | 1/12/2017 | 66
7 | ESP | Low Code Programme | Green | Business Case Development | 817708 | 343437.36 | 1/8/2017 | 1/8/2017 | -56
8 | ITA | Make model selection (IBM) | Green | Launch | 950738 | 684531.36 | 1/5/2017 | 1/9/2018 | 340
9 | PRT | Cloud Pilots | Red | Business Case Development | 713937 | 721076.37 | 1/10/2017 | 1/11/2017 | 36
10 | SVK | AI/Machine Learning | Red | Developing | 355725 | 412641 | 1/6/2017 | 1/12/2018 | 431
11 | BEL | Ignition Platform | Green | Testing | 945646 | 557931.14 | 1/4/2017 | 1/12/2017 | 66
12 | CYP | Ad Hoc | Green | Launch | 798583 | 367348.18 | 1/12/2017 | 1/12/2018 | 431
Formulas:
Runtime Left (Days) = [Expected End Date]-TODAY()

## Resources
Project_ID | first_name | last_name | job_title | Month
4 | Junie | Gillbee | Project Manager | 11 | 1 | Project Manager
11 | Trevar | Glidder | Business Analyst | 9 | 2 | Business Analyst
7 | Janie | Muzzullo | Solution Architect | 7 | 3 | Developer
2 | Chauncey | Forrest | Developer | 1 | 4 | Solution Architect
9 | Lev | Burds | Business Analyst | 2 | 5 | Tester
4 | Gary | Blabber | Project Manager | 6
12 | Farlee | MacKonochie | Tester | 4
6 | Wenda | Aisthorpe | Business Analyst | 10
5 | Andre | Keefe | Business Analyst | 8
1 | Artemas | McGlaughn | Tester | 11
12 | Cam | Bachman | Business Analyst | 3
2 | Kerrin | Meenan | Developer | 6
5 | Henrie | Worviell | Tester | 2
3 | Irvine | Swadlen | Business Analyst | 5
5 | Roxanna | Biskup | Developer | 12
2 | Robyn | Yousef | Solution Architect | 3
10 | Cyrillus | Tuppeny | Solution Architect | 11
3 | Keri | Pendlenton | Business Analyst | 5
11 | Hollyanne | Iglesia | Project Manager | 8
10 | Pandora | Edgeworth | Solution Architect | 7
3 | Gertruda | McReynold | Tester | 9
4 | Sylvester | Youde | Tester | 12
9 | Patsy | Dorricott | Tester | 6
10 | Kevan | Follit | Business Analyst | 6
11 | Cass | Haney | Developer | 5
4 | Austina | Rowet | Project Manager | 2
7 | Alonso | Rasher | Project Manager | 6
8 | Justinn | Bogace | Developer | 4
1 | Tildi | Seakin | Tester | 11
4 | Gallard | Braunthal | Solution Architect | 9
6 | Hayyim | Edworthy | Business Analyst | 6
2 | Rana | Measham | Solution Architect | 8
3 | Dorothea | Klimmek | Business Analyst | 3
5 | Debi | Brahan | Business Analyst | 6
5 | Barbie | Wolffers | Business Analyst | 11
7 | Maye | Aspall | Business Analyst | 9
9 | Johnna | Venable | Developer | 5
1 | Sidoney | MacCart | Developer | 10
2 | Ginger | Najara | Developer | 3
6 | Horatio | Grabb | Business Analyst | 11
4 | Analiese | Nare | Solution Architect | 7
7 | Ferdinand | Nulty | Developer | 12
7 | Nevins | Hirtzmann | Solution Architect | 7
3 | Micheline | Trumpeter | Business Analyst | 6
4 | Wheeler | Keasy | Solution Architect | 3
4 | Augustina | Britton | Business Analyst | 4
5 | Huntley | Latter | Business Analyst | 12
6 | Marti | Dudenie | Developer | 10
4 | Lark | Skeldon | Developer | 8
7 | Ariana | D'Abbot-Doyle | Developer | 7
5 | Ros | Abendroth | Developer | 9
6 | Ricki | Kettles | Business Analyst | 4
6 | Timotheus | Hindhaugh | Developer | 7
7 | Julie | Burge | Business Analyst | 3
5 | Arielle | Crock | Business Analyst | 6
4 | Lacie | Eldritt | Business Analyst | 10
4 | Patten | Dorney | Solution Architect | 8
5 | Merry | Daniellot | Solution Architect | 11
5 | Chryste | Graysmark | Solution Architect | 1
5 | Jeannette | Folger | Business Analyst | 1
7 | Maye | Roddam | Developer | 9
4 | Kayla | Ashburne | Solution Architect | 11
7 | Josi | McGeever | Developer | 4
5 | Leo | Borg-Bartolo | Developer | 9
7 | Herculie | Rathbone | Business Analyst | 9
4 | Kania | Stangoe | Business Analyst | 6
6 | Gregorio | Ruddoch | Business Analyst | 4
7 | Al | De Giovanni | Solution Architect | 7
6 | Lanie | Matiasek | Business Analyst | 5
7 | Jard | Beveredge | Solution Architect | 1
5 | Sharyl | Barrand | Solution Architect | 10
7 | Tobin | McFetrich | Solution Architect | 2
6 | Sollie | Swires | Solution Architect | 11
6 | Normie | McLagain | Business Analyst | 10
7 | Reese | Fardo | Developer | 7
5 | Carey | Fawkes | Developer | 2
8 | Leta | Chatelot | Developer | 11
8 | Hilda | Jelphs | Solution Architect | 12
4 | Tillie | Harding | Developer | 9
8 | Robers | Horsey | Developer | 8
4 | Egor | Yerson | Business Analyst | 11
4 | Hilly | Attiwill | Developer | 8
6 | Sean | O'Devey | Developer | 7
5 | Tiphanie | Gatty | Solution Architect | 5
4 | Redd | Allnutt | Solution Architect | 3
6 | Tabina | Cromack | Solution Architect | 6
6 | Rollie | Linklater | Business Analyst | 10
4 | Aldrich | Fishpool | Solution Architect | 7
5 | Charis | Donizeau | Business Analyst | 10
4 | Elianore | Ebbitt | Developer | 5
4 | Zerk | Matchitt | Developer | 4
5 | Nestor | Caress | Solution Architect | 10
7 | Margo | Draye | Business Analyst | 9
7 | Rosina | Zahor | Business Analyst | 12
8 | Teresita | Rean | Business Analyst | 4
6 | Crichton | Ovenell | Business Analyst | 8
4 | Corabelle | Celloni | Solution Architect | 7
8 | Lindsy | Mundford | Developer | 10
8 | Drucie | Perritt | Business Analyst | 2
7 | Portia | McKenney | Solution Architect | 7
7 | Delbert | Baggot | Solution Architect | 6
5 | Lulu | Borel | Developer | 1
5 | Arlina | Ladbrook | Solution Architect | 9
8 | Kennett | Britcher | Business Analyst | 11
5 | Cazzie | Stoffel | Solution Architect | 8
8 | Teressa | Polfer | Business Analyst | 5
5 | Selena | Badini | Business Analyst | 11
5 | Johannes | Heaps | Developer | 9
7 | Dino | Reichardt | Business Analyst | 2
8 | Alasteir | Cartmell | Solution Architect | 2
6 | Beatrice | Brugman | Developer | 2
6 | Farrel | Klampk | Developer | 5
4 | Paco | Naris | Developer | 8
6 | Mellicent | Beceril | Developer | 6
7 | Van | Kurdani | Business Analyst | 2
8 | Abeu | Abberley | Developer | 8
4 | Margery | De la Yglesia | Business Analyst | 9
7 | Ber | Geibel | Business Analyst | 7
8 | Rosemonde | Watford | Business Analyst | 7
4 | Killie | Fenelon | Business Analyst | 11
8 | Dennet | Pavkovic | Developer | 2
6 | Kelsy | Eadington | Solution Architect | 12
7 | Davita | Duncanson | Solution Architect | 5
4 | Orton | Thorn | Business Analyst | 8
7 | Palm | Goodlet | Developer | 6
6 | Wendel | Piddlehinton | Developer | 6
4 | Brion | Downage | Solution Architect | 12
8 | Dulcea | Mitroshinov | Business Analyst | 2
4 | Marilyn | Ayce | Developer | 3
7 | Anette | Ledley | Solution Architect | 12
4 | Skylar | Demongeot | Solution Architect | 5
6 | Ernest | Van der Velden | Business Analyst | 2
4 | Dukey | Tolworthie | Developer | 10
4 | Jozef | Darragon | Business Analyst | 6
5 | Enrica | Huntley | Business Analyst | 5
8 | Gerianne | Widdecombe | Developer | 2
6 | Lennard | Kristufek | Business Analyst | 2
4 | Tomkin | Tuite | Developer | 8
8 | Christin | Malling | Developer | 1
8 | Xavier | Bellis | Business Analyst | 11
6 | Humberto | Grimmett | Developer | 1
8 | Arleta | Limbourne | Business Analyst | 6
8 | Ogdan | Girkin | Developer | 8
6 | Shirline | Kiraly | Solution Architect | 12
7 | Poul | Mirrlees | Solution Architect | 9
7 | Colly | Broke | Solution Architect | 7
7 | Dorri | Jolliman | Developer | 3
4 | Addison | Caudray | Business Analyst | 8
6 | Kennett | Outerbridge | Business Analyst | 2
8 | Tobye | Quadri | Business Analyst | 11
7 | Caldwell | Ruggles | Business Analyst | 9
4 | Chloris | Mayo | Developer | 10
5 | Garfield | Shackleton | Business Analyst | 1
8 | Thadeus | Jorden | Solution Architect | 7
4 | Norma | Skipworth | Business Analyst | 3
7 | Elsinore | Foale | Developer | 8
4 | Ermengarde | Hammerberger | Business Analyst | 2
4 | Ivory | Cowper | Solution Architect | 1
5 | Codee | Treweek | Business Analyst | 10
5 | Erastus | Balshaw | Solution Architect | 8
7 | Avery | Banbridge | Solution Architect | 6
3 | Annemarie | Sertin | Solution Architect | 8
9 | Hillary | Leggis | Solution Architect | 12
4 | Hayes | Vyvyan | Developer | 8
10 | Desi | McElhinney | Business Analyst | 4
4 | Penrod | Forton | Developer | 10
3 | Kain | Rickards | Business Analyst | 1
1 | Emilee | Cleare | Developer | 12
7 | Pancho | Battison | Business Analyst | 7
4 | Datha | Mityushin | Business Analyst | 3
1 | Keene | Bailes | Solution Architect | 10
11 | Nyssa | McTeer | Business Analyst | 12
9 | Bord | Aizik | Solution Architect | 7
2 | Gerrard | Colebourne | Developer | 3
10 | Gualterio | Edgeworth | Developer | 12
9 | Garret | Osbourn | Business Analyst | 1
8 | Juana | Le Gall | Developer | 1
1 | Junie | Gillbee | Solution Architect | 8
10 | Trevar | Glidder | Business Analyst | 7
1 | Janie | Muzzullo | Solution Architect | 12
4 | Chauncey | Forrest | Developer | 7
6 | Lev | Burds | Developer | 11
12 | Gary | Blabber | Solution Architect | 4
8 | Farlee | MacKonochie | Developer | 12
11 | Wenda | Aisthorpe | Solution Architect | 4
1 | Andre | Keefe | Developer | 12
1 | Artemas | McGlaughn | Business Analyst | 3
1 | Cam | Bachman | Developer | 2
8 | Kerrin | Meenan | Developer | 3
6 | Henrie | Worviell | Solution Architect | 1
9 | Irvine | Swadlen | Business Analyst | 6
11 | Roxanna | Biskup | Business Analyst | 4
5 | Robyn | Yousef | Developer | 10
2 | Cyrillus | Tuppeny | Business Analyst | 12
4 | Keri | Pendlenton | Project Manager | 10
9 | Hollyanne | Iglesia | Developer | 9
4 | Pandora | Edgeworth | Project Manager | 12
12 | Gertruda | McReynold | Developer | 5
11 | Sylvester | Youde | Developer | 12
8 | Patsy | Dorricott | Tester | 7
8 | Kevan | Follit | Developer | 4
9 | Cass | Haney | Solution Architect | 5
4 | Austina | Rowet | Project Manager | 12
7 | Alonso | Rasher | Tester | 4
8 | Justinn | Bogace | Project Manager | 7
9 | Tildi | Seakin | Project Manager | 7
6 | Gallard | Braunthal | Business Analyst | 9
1 | Hayyim | Edworthy | Business Analyst | 8
1 | Rana | Measham | Tester | 7
1 | Dorothea | Klimmek | Business Analyst | 12
1 | Debi | Brahan | Business Analyst | 6
1 | Barbie | Wolffers | Solution Architect | 12
1 | Maye | Aspall | Solution Architect | 12
1 | Johnna | Venable | Tester | 5
1 | Sidoney | MacCart | Business Analyst | 8
1 | Ginger | Najara | Developer | 7
1 | Horatio | Grabb | Business Analyst | 2
1 | Analiese | Nare | Developer | 2
1 | Ferdinand | Nulty | Developer | 10
1 | Nevins | Hirtzmann | Tester | 4